## Sheet1
ITSC-3155 Software Engineering
Sprint#2
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status
User Story: Guest Order Placement | 8 | Dev | 19 | 7.5 | 6 | 11 | 1 | 1 | 0 | Done
Coding |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 0
Code Review |  |  | 8 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 0
Testing |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0 | Doing | 0
Integration |  |  | 3 | 1 | 2 | 3 | 1 | 0 | 0 | Doing | 0
User Story: Menu Management | 10 | Abhi | 27 | 15 | 19.5 | 6.5 | 3 | 1 | 0 | Done
Coding |  |  | 10 | 3 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
Code Review |  |  | 4 | 5 | 5 | 1 | 1 | 1 | 0 | Done | 0
Testing |  |  | 8 | 2 | 5 | 0 | 1 | 0 | 0 | Done | 1
Integration |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 0 | Done | 1
User Story: Order Tracking System | 7 | Tasnim | 17.5 | 8.5 | 3.5 | 3.5 | 4 | 1 | 0 | Doing
Coding |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0 | Done | 0
Code Review |  |  | 6 | 1 | 3 | 3 | 3 | 0 | 0 | Done | 0
Testing |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | Done | 0
Integration |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | Doing | 3
User Story: Payment Processing | 9 | Bhavith | 25.5 | 12.5 | 13.5 | 13.5 | 5 | 2 | 0 | Doing
Coding |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0 | Doing | 0
Code Review |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 0 | Doing | 1
Testing |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 0 | Doing | 1
Integration |  |  | 4.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  |  | 0
User Story: Customer Feedback System | 5 | Dev | 18 | 7.5 | 6 | 11 | 1 | 1 | 0 | Doing
Coding |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 0
Code Review |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 0
Testing |  |  | 5 | 0.5 | 0 | 3 | 0 | 0 | 0 | Done | 0
Integration |  |  | 3 | 1 | 2 | 3 | 1 | 0 | 0 | Doing | 0
User Story: Real-Time Order Notifications | 6 | Abhi | 27 | 15 | 19.5 | 6.5 | 3 | 1 | 0 | Done
Coding |  |  | 10 | 3 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
Code Review |  |  | 2 | 5 | 5 | 1 | 1 | 1 | 0 | Done | 0
Testing |  |  | 8 | 2 | 5 | 0 | 1 | 0 | 0 | Done | 1
Integration |  |  | 2 | 5 | 9 | 5 | 1 | 0 | 0 | Doing | 1
User Story: Promo Code Management | 4 | Tasnim | 13 | 8.5 | 3.5 | 3.5 | 4 | 1 | 0 | Doing
Coding |  |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Doing | 0
Code Review |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0 | Doing | 0
Testing |  |  | 2 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | Doing | 0
Integration |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | Doing | 3
User Story: Analytics Dashboard | 12 | Bhavith | 30 | 12.5 | 13.5 | 13.5 | 5 | 2 | 0 | Doing
Coding |  |  | 15 | 4 | 2 | 2 | 1 | 1 | 0 | Doing | 0
Code Review |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 0 | Doing | 1
Testing |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 0 | Doing | 1
Integration |  |  | 3 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Doing | 0
TOTAL |  |  | 177 | 87 | 85 | 69 | 26 | 10 | 0 |  | 18